## 1. Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US_01 | As a developer, I want to collect and preprocess KYC data (Aadhaar, bills) so that AI models can use clean input | Must Have | Data availability | Backend Team | Completed
Sprint 2 | Sprint 2 | US_02 | As a data scientist, I want to build AI models (NLP, CNN, GNN) for identity and address verification | Must Have | Cleaned data from Sprint 1 | Backend Team | Completed
Sprint 3 | Sprint 3 | US_03 | As a compliance analyst, I want to integrate fraud detection pipeline with AML/KYC systems for real-time validation | Should Have | Model outputs | Full Stack Team | Completed
Sprint 4 | Sprint 4 | US_04 | As a user, I want a web dashboard to upload documents and visualize fraud results | Must Have | Backend APIs | Frontend Team | Completed
Sprint 4 | Sprint 4 | US_05 | As a developer, I want to deploy the full pipeline and validate results with synthetic Aadhaar data | Must Have | All previous sprints | DevOps Team | Completed

## 2. Sprint Backlog
US_ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
US_02 | T_01 | Build OCR extraction module | 2025-01-09 | 2025-03-09 | Ravi | Development | Completed | 8 | Day 1: Done; Day 2: Done
US_02 | T_02 | Fine-tune NLP model for address verification | 2025-03-09 | 2025-06-09 | Sneha | Model Training | Completed | 12 | Day 2: Done; Day 3: Done; Day 4: Done
US_02 | T_03 | Train CNN model to detect document tampering | 2025-06-09 | 2025-09-09 | Bhanu | Model Training | Completed | 10 | Day 3: Done; Day 4: Done; Day 5: Done
US_02 | T_04 | Train GNN model to detect duplicate Aadhaar identities | 2025-09-09 | 2025-12-09 | Arjun | Research/Implementation | Completed | 14 | Day 4: Done; Day 5: Done; Day 6: Done; Day 7: Done
US_02 | T_05 | Validate models and compare accuracy | 2025-12-09 | 14/09/2025 | Team | Testing | Completed | 6 | Day 7: Done; Day 8: Done; Day 9: Done; Day 10: Done

## 3. Daily StandUp Report
Sprint | Day | Impediments | Action Taken
Sprint 3 | Day 1 | Integration with backend API not responding | Fixed endpoint mapping in Flask routes
Sprint 3 | Day 2 | Fraud detection API taking too long to respond | Optimized model inference time
Sprint 3 | Day 3 | Missing AML rules data for testing | Created synthetic AML rule dataset
Sprint 3 | Day 4 | API authentication errors | Added JWT-based auth layer
Sprint 3 | Day 5 | Everything functional | Proceeded with testing pipeline

## 4. Sprint Retrospective
SL. | Sprint | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 4 | 20/09/2025 | 2025-04-10 | Group A – Backend | Start writing modularized APIs | Stop skipping documentation | Continue collaborating across frontend-backend | Created proper README & module docstrings
2 | Sprint 4 | 20/09/2025 | 2025-04-10 | Group A – Frontend | Start using responsive UI components | Stop making UI directly from backend responses | Continue improving user-friendly dashboards | Added validation screens & error messages
3 | Sprint 4 | 20/09/2025 | 2025-04-10 | Group B – Backend | Start containerizing deployment | Stop using local JSON for AML data | Continue focusing on clean code | Created Docker container for backend
4 | Sprint 4 | 20/09/2025 | 2025-04-10 | Group B – Frontend | Start implementing toast notifications | Stop using hardcoded endpoints | Continue enhancing UX | Improved navigation and visual consistency

## 5. Defect Tracker
SI No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Remarks
1 | Vanshika Dureja | 2025-03-09 | OCR output not extracting full address from Aadhaar image | Sprint 1 | Backend Team | Functional | Improved preprocessing and added Tesseract config for multi-line extraction | 2025-04-09 | Closed | Verified successfully
2 | Vanshika Dureja | 2025-07-09 | Model output returning inconsistent address verification scores | Sprint 2 | Backend Team | Algorithmic | Adjusted threshold values and retrained model | 2025-08-09 | Closed | Performance improved
3 | Vanshika Dureja | 2025-10-09 | Frontend not displaying fraud prediction results correctly | Sprint 2 | Frontend Team | UI/Integration | Fixed JSON parsing and updated API endpoint in React | 2025-11-09 | Closed | Tested and verified
4 | Vanshika Dureja | 13/09/2025 | GNN model showing NaN values during training | Sprint 2 | Backend Team | Model Training | Normalized data and fixed null entries in graph edges | 14/09/2025 | Closed | Stable model output
5 | Vanshika Dureja | 18/09/2025 | AML check module failing on duplicate address input | Sprint 3 | Backend Team | Logic | Added address hashing and duplicate detection rule | 19/09/2025 | Closed | Verified via testing
6 | Vanshika Dureja | 21/09/2025 | Upload form not handling invalid file formats | Sprint 3 | Frontend Team | UI/Validation | Added MIME type check and error popup | 22/09/2025 | Closed | User-friendly validation added
7 | Vanshika Dureja | 25/09/2025 | Real-time pipeline response delay | Sprint 3 | Backend Team | Performance | Implemented async processing and caching | 26/09/2025 | Closed | Latency reduced by 35%
8 | Vanshika Dureja | 2025-01-10 | Dashboard graphs not updating after backend changes | Sprint 4 | Frontend Team | Integration | Re-linked data binding with new API route | 2025-02-10 | Closed | Graph sync issue resolved
9 | Vanshika Dureja | 2025-03-10 | Fraud alerts not showing in admin view | Sprint 4 | Backend Team | Functional | Fixed alert trigger logic in API | 2025-04-10 | Closed | Verified
10 | Vanshika Dureja | 2025-05-10 | Minor typo and alignment issues in UI | Sprint 4 | Frontend Team | UI | Adjusted CSS layout and corrected labels | 2025-06-10 | Closed | Presentation-ready